## Checklist
Pneumonia Detection
Vikas Ramaswamy |  |  |  | cc: Firmenbetreuer
Matr.-Nr | 7024164 |  |  | Projektpartner
Erstprüfer
Checklist
update every day!
No. | Topic | done | date
First two weeks
1 | read ProjectManagement/BestPractice.pdf | Done | 2023-03-07
2 | fulfill author.xlsx | Done | 2023-03-07
3 | Install TeXLive | Done | 2023-03-07
4 | install TeXStudio | Done | 2023-03-07
5 | install Sumatrapdf | Done | 2023-03-07
6 | configure TeXStudio | Done | 2023-03-07
7 | test template report | Done | 2023-03-11
8 | test template poster | Done | 2023-03-11
9 | test template Presentations/template | Done | 2023-03-11
10 | install doxygen | Done | 2023-03-11
11 | literature research | Done | 2023-03-21
12 | presentation "Literature" | Done | 2023-03-22
13 | write n introduction | Done | 2023-04-03
14 | presentation "Introduction" | Done | 2023-04-18
15 | project plan | Done | 2023-04-30
16 | fulfill the list "Resulting Objects" | Done | 2023-05-05
17 | presentation "Project Plan" | Done
18 | update project plan | Done | 2023-05-01
19 | update the list "Resulting Objects" | Done | 2023-05-06
20 | presentation "Project Plan" II | Done
21 | rename all tex files along the project plan | Done | 2023-05-01
22 | delete or add additional TeX or Python projects, e.g. Manual | Done | 2023-05-06
23 | update README.md | Done | 2023-05-06
24 | update the checklist | Done | 2023-05-06
Processing the project
25
26
27 | work along the project plan | Done
28 | update github every day | Done
29
30
Final stage
31 | check: all website as pdf-file? | Done | 2023-05-06
32 | check: all pdfs in the folder Documents? | Done | 2023-05-06
33 | check: all images okay? | Done | 2023-05-06
34 | check spelling | Done | 2023-05-06
35 | check: poster? | Done
36 | print poster | Done
37 | check: GitHub project | Done | 2023-05-07
38 | ready minimal one day before deadline | Done | 2023-05-06
39
40
41
42

## Projekt Plan V1.0 (deut.)
Das Liebesleben der Maikäfer bei Nacht
|  | KW | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | ... | 26 | 27 | ... | 30
|  | lfd. Woche | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | ... | 16 | 17 | ... | 20
TP-Nr. | TP-Name | Dauer
1 | Einarbeitung / Literatur | 2.5
2 | ... | 1
3 | ... | ...
4 |  | 2
5 |  | ...
6
7
8
9
10
11
12
13
14 | Verfassen PA / BT / DA / MT | ...
15 | Durchsicht | 2
16 |  | 1.5
17 | Kolloquium | 1
| Urlaub / Feiertage | [5 empty] | Geburt |  |  | Ostern |  | Pfingsten
| Anmeldung / Abgabe | [7 empty] | 34. März |  |  |  |  | 34. Juli
Besprechungen
PJ = Projekt
| TP = Teilprojekt | [8 empty] | x = f(Studiengang)
Anmeldung
Abgabe
Hermann Meyer
Matr.-Nr. 1112569
7. Sem PVT
Version: 1.3 / 29.02.2025
Persönliche Daten
Vorläufiger Titel
der Arbeit
Nr. des Teilprojektes
(10 - 20 incl. Kolloquium)
Bezeichnung des Teilprojektes
Kalenderwoche des Jahres = zeitl. Lage
Laufende Woche der Arbeit seit Start => Dauer
planbare Ausfallzeiten
(selbst, Partner, Prüfer)
Anmeldetermin = gepl. Abgabetermin
abzgl. x Monate (für BT/DA/MT)
geplanter Abgabetermin
Teilprojekt
Balkenlänge = geschätzte Dauer; kleinste Einheit = 0,5 Wochen
subjektiver Abarbeitungzustand des TP bei korrelierender Besprechung
gepl. Besprechungstermin mit Erstprüfer
Planungsstand des Projektplans (Version, Datum)
spontan + intuitiv geschätzte Dauer des TP;
kleinste Einheit = 0,5 Wochen
Projektplan-Muster für eine Projektarbeit (PA) / Bachelor Thesis (BT) / Diplomarbeit (DA) / Master Thesis (MT)
cc: - Firmen-Betreuer
- PJ-Partner
- Erstprüfer
Empfänger
des PJ-Plans
Plan hier: Bearbeitung wegen Auszeit unterbrechen
Plan hier: Bearbeitung trotz Feiertage fortführen
1
2
2
3
5
4
6
7
8
9
10v
11v

## Project Plan V1.0 (eng.)
The Love Life of Cockchafers at Night
|  | Week of Year | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | ... | 35 | 36 | ... | 39
|  | Project Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | ... | 26 | 27 | ... | 30
SP No. | SP's Title | Duration
1 | Informative activities / literature | 2.5
2 | ... | 1
3 | ... | ...
4 |  | 2
5 |  | ...
6
7
8
9
10
11
12
13
14 | Writing of thesis | ...
15 | First checking through by examiner | 2
16 | Optimization | 1.5
17 | Colloquium | 1
| Vacation / holidays | [5 empty] | Birth |  |  | Easter |  | Pentecost
| Enrolement / Submission | [7 empty] | March 34 |  |  |  |  | July 34
Meetings
SP = Sub-project
x = f(course of study)
Enrolement
Submission
Hermann Meyer
Matr.-Nr. 1112569
7. Sem PVT
Version: 1.0 / 29.02.2025
Personal Data
Preliminary title
of thesis
SP's number
(10 - 20 SPs incl. Colloquium)
SP's title
Week of year
Weeks since start of project => duration
schedulable time outs
(causes: yourself, partners, examiner, ..)
Date of enrolement = scheduled date of submission minus x months
scheduled date of submission
SP
Length of bar = estimated duration; smallest unit = 0.5 week
Actual state of SP's completion at time of corresponding meeting
(subjective estimation)
Scheduled meeting with first examiner
Project plan of (version / date)
Duration of SP estimated in the beginning
(spontaneously and intuitivly)
smallest unit = 0,5 week
Template for Project Plan of Master's Thesis
cc: - Contact person in company
- Project partner
- First examiner
Receivers of this project plan
Scheduled interruption of work
Scheduled to continue work despite of holiday
Colloquium
1
2
2
3
5
4
6
7
8
9
10v
11v

## Resulting objects
Pneumonia Detection
Sangram Patil |  |  |  | cc: Firmenbetreuer
Matr.-Nr | 7023678 |  |  | Projektpartner
Erstprüfer
List of all Resulting Objects
Subtask | Resulting objects | done | date
Literature | List of keywords
Brief description of the sources
bib file
Bibliography in the report
pdf documents
quality check
…
Problem Description | Done in the final report ".\report" on the section "1 Introduction" | Done | 2023-03-24
Challenges | Done in the final report ".\report" on the section "1 Introduction" | Done | 2023-03-24
Proposed Solution | Done in the final report ".\report" on the section "1 Introduction" | Done | 2023-03-26
Data Type | Done in the final report ".\report" on the section "2 Domain Knowledge" | Done | 2023-04-02
Data acquisition | Done in the final report ".\report" on the section "2 Domain Knowledge" | Done | 2023-04-03
Data Quantity | Done in the final report ".\report" on the section "2 Domain Knowledge" | Done | 2023-04-05
Data Quality | Done in the final report ".\report" on the section "2 Domain Knowledge" | Done | 2023-04-05
Algorithms | Done in the final report ".\report" on the section "5 Data Mining" | Done | 2023-04-08
Hyperparameters | Done in the final report ".\report" on the section "5 Data Mining" | Done | 2023-04-12
Relevance | Done in the final report ".\report" on the section "5 Data Mining" | Done | 2023-04-13
Requirements | Done in the final report ".\report" on the section "5 Data Mining" | Done | 2023-04-16
KDD process | Done in the final report ".\report" on the section "4 Knowledge Discovery in Databases Process" | Done | 2023-04-02
Data Selection | Done in the final report ".\report" on the section "6 Development" | Done | 2023-04-21
Data Preprocessing | Done in the final report ".\report" on the section "6 Development" | Done | 2023-04-23
data transformation | Done in the final report ".\report" on the section "6 Development" | Done | 2023-04-25
data mining | Done in the final report ".\report" on the section "6 Development" | Done | 2023-04-28
Evaluation | Done in the final report ".\report" on the section "8 Open Question" | Done | 2023-05-01
Validation | Done in the final report ".\report" on the section "8 Open Question" | Done | 2023-05-03
Deployment | Done in the final report ".\report" on the section "7 Development" | Done | 2023-05-05
Work flowchart | Done in the final report ".\report" on the section "7 Development" | Done | 2023-05-05
Conclusions | Done in the final report ".\report" on the section "9 Conclusions " | Done | 2023-05-06
Future Work | Done in the final report ".\report" on the section "9 Conclusions " | Done | 2023-05-06
Projectplan-Project (10credits) in Master Course "Business Intelligence and Data Analytics"